## Sheet1
Card | Story | Back of the card | Task | Status | Estimated Time
Card 1 | As a user I want to view the inventory so that I can see all the available products. | Inventory should be displayed. All details of products are showen. | Create Inventory, product and Inventory_Management class. | Done | 2 days
|  |  | Create add_Products(),for taking all inputs of product form user. | Done
|  |  | Create add_Product_to_File(), for recording product details to file(ID, name, number of items, price). | Done
|  |  | Create save_all_Products_to_File(), save array of products to file. | Done
Card 2 | As a user I wat to login so I can get access to the inventory. | The main menu prompts user to choose its role to login with.The user enters its credentials. The system validates user name and password and lets the user in after validating. | Create User, User_Management and User_Type (Enum) classes. | Done | 2 days
|  |  | Create get_all_Users_to_File() to get all users from file at start of application. | Done
|  |  | get_User_with_Username(), to get user whose user name matches with the given user name. | Done
Card 3 | As a user (admin)I want to be able to add new users(cashirs and managers) So that work finishe on time. | The user must be loged in first.The user chooses which categori to add a user to.Fill the user details. | Using User, User_Management and User_Type (Enum) classes as in story 2. | Done | 0.5 day
|  |  | add_User(), to take all inputs of user, create user object and save it to file. | Done
|  |  | view_User(), to view all users. | Done
Card 4 | as a user I want to be able to sale an item so that I increase the profit. | The user must be loged in first. the user can choose an item from inventory. the inventory must be updated and there should be always one item for each product. | Related Classes:Product, Inventory,Inventory_Management | Done | 1 days
|  |  | Create Transaction and Transaction_Management classes to add the sold item to transaction list. | Done
|  |  | view_Inventory(), to view complete inventory. | Done
|  |  | sale_item(), for taking input which item to sale and number of items to sale. | Done
Card 5 | As a user I want to be able to return an Item so that can have my money back. | The user must be loged in first. all the sold items being displayed. the user enters the required recipet number, the item removes from the transaction and the inventory being updated again. | Related Classes:Product, Inventory,Inventory_Management,Transaction and Transaction_Management classes. | Done | 2 days
|  |  | return_an_item(), to take input which product to return back and number of items to return back and updates the transaction. updates the inventory. | Done
Card 6 | As a user I want to view the sold out items so that I order new items again. | The user must be loged in first.the system displayes the sold out items if any.the user makes an order for that item. | Related Classes:Product, Inventory,Inventory_Management and Order | Done | 1.5 days
|  |  | Create view_all_Sold_out_Product(), to view products that have only one item left. | Done
|  |  | Order_the_Item(), to order the product and number of items to purchase. records it in file. | Done
|  |  | save_all_Orders_to_File(), to save array of orders object to file. | Done
Card 7 | As a user(manager) I want to be able to view the order list so that I decide to order or not. | The user must be loged in first. the add diplays list of all items being ordered. | Related Classes:Order, Inventory, Product and Manager_Menu | Done | 0.5 day
|  |  | fetch_all_Orders_from_File(), to get all orders from file. | Done
|  |  | save_Order_to_File(), to save single object to file. | Done
Card 8 | As a user I want to be able to pay salaries to my employees so that everyone is staisfied. | The user must be loged in first. choose the emplooyee from the list, enter the salary. | Using User and User_Management classes. | Done | 0.5 day
|  |  | Using view_User(), to view all users. | Done
|  |  | pay_salary() method, to pay salary to any employee. | Done
Card 9 | As a user I want to see the profits and best sellers so that I can add more such products | The user must be loged in first. view the profits and best sells items. | Related Classes:Inventory, Inventory_Managerment, Order_Management, Transaction_Management | Done | 0.5 day
|  |  | view_all_Transactions(), to view all transactions. | Done
|  |  | best_Selling_Product(), to get the statistics about which product has higher sales and which has lower sales. | Done
Card 10 | As a user I want to communicate with my collegues via a chat channel so that I save more time. | The user must be loged in first. enter the chat and choose the user to send message to. |  | Not Done